## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Assigned Group Member
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Project1 | fill in requirements from last submission | 1.5 | 0 | 0 | 0 | 0 | Will
Cook | to see what food is available | 3 | 1.5 | 0 | 0 | 0 | Joshua
Cook | to retrieve food | 2 | 2 | 2 | 0.5 | 0 | Joshua
Officer | to see what munitions are available | 3 | 1.5 | 0 | 0 | 0 | Nick
Officer | to retrieve munitions | 2 | 2 | 0 | 0 | 0 | Nick
Crewmate | to report damage | 2 | 2 | 0.5 | 0 | 0 | Victor
Cook | view report of the remaining time until expiration date | 2 | 2 | 2 | 1 | 0 | Victor
Quartermaster | to be able to report theft | 3 | 1.5 | 0 | 0 | 0 | Will
Officer | to see a report of any occurences of theft | 2 | 2 | 2 | 0.5 | 0 | Will
| Estimate Totals | 20.5 | 14.5 | 6.5 | 2 | 0